## Sheet1
RECOVERY/eNSR TO DO'S
Task | People Involved | Due Date | Notes
Sharpen line cutter heads | John | Wednesday, 9/6
Purchasing items for the weight | William | Tuesday, 9/5 | Two sand bags, sand, a way to attach the bag to the carabiner
Print another eNSR cap | Marie | Thursday, 9/7
Mill out a small portion of the surgical tubing ring so that the RMAs can fully extend | William or John | Wednesday, 9/6 | Please establish who is the owner of this task and let Marie know
Lubrication for the motor | William | Today or Tuesday | Need this in order to make a decision about changing the motor; only today if Eric is working on campus
Try to improve the motor using the controller | Eric | Tuesday, 9/5 | Need this in order to make a decision about changing the motor
Learn how to operate the controller and get feedback | Eric, Marie, John, William | Tuesday, 9/5 | We will do this at the Tuesday night mtg
Finalize voltage applied to line cutters | Eric and John | Thursday, 9/7 | Try to gather more documentation on the line cutters during this (cutting quality, voltage used/time used, etc.)
Buy a new, better quality audio cable | Eric | Tuesday, 9/5 | If it's not too spendy, get it shipped quick
Run code more to make sure it is consistent/smooth; mitigate faults | Eric | Thursday, 9/7 | Maybe have someone else run through the code as a second set of eyes? Maybe Miles or Andrew?
Rewrite code to not just brute force motor time length | Eric | Friday, 9/8 | Maybe talk this one through with Andrew for any other strategies?
TESTING | Eric, Marie, John, William | Friday, 9/8 TIME TBD | This will include the controller turning the motor, releasing the upper ring, which will allow the nosecone to pop off and flip up the drogue cup in the process; line cutters should already have been tested to confidence the day before